## Current Iteration
|  | Iteration Number: |  |  |  | 2
|  | Expected Total effort: |  |  |  | 37
|  | Days In Sprint: |  |  |  | 5
Burndown Chart 10/10/2019 - 15/10/2019
User Stories |  | Days (Points Completed) | [19 empty] | Remaining
Sprint Backlog Items | Beginning Balance | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Task Balance | Percentage Completed
GUI prototype for visning af den enkelte film med mulighed for køb af billeter til film | 5 | Days (Points Completed) 1: 5 | 0 | 100%
GUI prototype for valg af sal | 5 | [20 empty] | 5 | 0%
GUI prototype for valg af sæde | 5 | [20 empty] | 5 | 0%
GUI prototype for køb af billet(er) med mulighed for at indtaste kundeoplysninger | 5 | [20 empty] | 5 | 0%
GUI prototype for kvittering | 5 | [20 empty] | 5 | 0%
POJO for billet | 1 | [20 empty] | 0 | 100% | bar: Days (Points Completed) 1
POJO for sal | 1 | [20 empty] | 0 | 100% | bar: Days (Points Completed) 1
POJO for sæde | 1 | [20 empty] | 0 | 100% | bar: Days (Points Completed) 1
POJO for kvittering | 1 | [20 empty] | 0 | 100% | bar: Days (Points Completed) 1
Kodning og routing af controllers så GUI af køb billet kan vises | 5 | [20 empty] | 5 | 0%
POJO for forestilling | 3 | Days (Points Completed) 1: 3 | 0 | 100%
Feature 12 | [21 empty] | 0
Feature 13 | [21 empty] | 0
Feature 14 | [21 empty] | 0
Feature 15 | [21 empty] | 0
Feature 16 | [21 empty] | 0
Feature 17 | [21 empty] | 0
Feature 18 | [21 empty] | 0
Feature 19 | [21 empty] | 0
Feature 20 | [21 empty] | 0
Feature 21 | [21 empty] | 0
Feature 22 | [21 empty] | 0
Feature 23 | [21 empty] | 0
Feature 24 | [21 empty] | 0
Feature 25 | [21 empty] | 0
Feature 26 | [21 empty] | 0
Feature 27 | [21 empty] | 0
Feature 28 | [21 empty] | 0
Feature 29 | [21 empty] | 0
Feature 30 | [21 empty] | 0
Effort Remaining | 37 | 25 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 25 | 32.43%
Ideal Trend | 37 | 29.6 | 22.2 | 14.8 | 7.4 | 1.7764e-15 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
Note on G4: For an Accurate Burndown Chart and Ideal Trend, Fill in the expected working days in an Iteration (1 Week = 5 Days). You can additionally choose to hide columns that are not needed. If your Iteration is 2 weeks long, you can hide columns M through V and place 10 in this box. Default Formula Assumes 20 days